The Columbia University Libraries

The Andrew W. Mellon Foundation

Scholarly Communications Program

Grant Project Title: 		Preserving Historic Audio Content

Developing Infrastructures and Practices for Digital Conversion

Name of Institution: 		Trustees of Columbia University in the City of New York

Contact Information: 	Principal Investigator:

Janet E. Gertz

Director, Preservation and Digital Conversion Division

Columbia University, Butler Library 101C

535 West 114th Street, Mail Code 1108

New York, NY 10027

gertz@columbia.edu

(212) 854-5757

Office of Research Administration:

Patricia Valencia

Project Officer

Columbia University, 254 Engineering Terrace

1210 Amsterdam Avenue, Mail Code 2205

New York, NY 10027

pv122@columbia.edu

(212) 854-0371

Date of Submission:		March 13, 2008

Project Dates:		July 1, 2008–June 30, 2010

Preserving Historic Audio Content:

Developing Infrastructures and Practices for Digital Conversion

Project Summary

Preserving audio recordings is of increasing importance as the high risk of loss of valuable content becomes widely understood.  Many institutions with historic audio content are eager to begin digital conversion, but are impeded by a number of obstacles to successful preservation of audio content, particularly in the areas of metadata and management of the digital files.

The Columbia University Libraries wishes to preserve 820 audiotapes from the Oral History Research Office comprising approximately 1,200 hours, but we must build a fully functional infrastructure for audio preservation in order to do so.  The tapes have been identified as both of the highest potential research value and at the highest risk for deterioration and loss.

Among the recordings are oral histories of politically and socially active figures such as Nikita Khrushchev, Walter Lippmann, George Meaney, Clarence Mitchell, Nelson Rockefeller, Gloria Steinem, Robert F. Wagner; historians and literary figures such as James Baldwin, Jacques Barzun, Isaiah Berlin, William Buckley, Robert Heilbronner, Irving Howe, Anita Loos, Arthur Schlesinger Jr., Isaac Bashevis Singer, C. Vann Woodward; and members of the arts and entertainment community such as Judith Anderson, Gene Autry, Frank Capra, Joseph Cotton, Joel McCrea, Otto Preminger, Richard Rogers, Virgil Thomson, Mies van der Rohe, King Vidor.

We propose a two-year project, with work beginning in July 2008:

- We will select a group of high-priority audio materials totaling 1,200 hours as a target 
for the project and will move them through the steps of digital conversion and metadata creation;

- We will attempt to build an infrastructure model for institutions that do not have an 
in-house audio conversion lab;

- We will collaborate with expert consultants and a leading service provider for audio preservation conversion to develop practices that are mutually functional for both content-owning institutions and service providers;

- We will disseminate the activities of the project through written reports and presentations to appropriate professional organizations; and

- We will build and continually maintain a public project web site with full information about the project, including the final proposal and documentation created during the project.

This project will result in the following outcomes:

- Preservation through digital conversion of 1,200 hours of seriously endangered analog audio recordings that have been identified as important for future research;

- Creation of cataloging records and other metadata to facilitate discovery of the preserved content by scholars, and to support preservation of the digital versions;

- Establishment at Columbia of a carefully designed and fully functional audio preservation infrastructure that is in compliance with current best practices and incorporates smooth working relations with an external service provider; and

- Creation and ongoing maintenance of a public project web site.

Rationale for the Project

Obstacles to Audio Preservation

Preserving audio recordings is of increasing importance as the high risk of losing valuable content becomes widely understood.  Many institutions that hold historic audio content are eager to take action, but they are impeded by a number of obstacles to successful preservation of their audio content.

Identification of at-risk recordings

Many institutions do not have detailed inventories of their audio recordings and are even less well informed as to priorities for preservation.  As one response to this situation, Columbia has undertaken the current Project to Survey the Audio and Moving Image Collections, with the Mellon Foundation’s generous assistance.  We have developed a survey tool optimized for these materials that evaluates degrees of risk of physical deterioration and obsolescence.  Starting from this physical basis, we have examined all of our unique analog audio items and determined the relative importance of the content for future research.  Preliminary versions of the survey tool have been presented at conferences of the American Library Association (ALA), Association of Moving Image Archivists (AMIA), and the International Association of Sound and Audiovisual Archives (IASA) to a high degree of interest, and we will make the survey tool and instruction manual freely available to all interested institutions this spring when the project is completed.

Standards and best practices for digital audio conversion and metadata

There is now general agreement that 96 kHz, 24 bit word Broadcast Wave files are the appropriate vehicle for high-quality audio conversion.  However, best practices and standards for technical capture and structural metadata are still evolving.  The Audio Engineering Society (AES) and other organizations are bringing out documents that provide a framework within which best practices can be developed, but a good deal of work remains to be done.

Preservation of the digitized audio content

No matter how high the quality of conversion, preservation of the audio content results only when systems for long-term management of the digital files are in place, including digital asset management systems, preservation-specific metadata, and trusted digital archives.  While this situation is general to all digital preservation, there is a need to assure that audio files and their metadata are compatible with METS (Metadata Encoding and Transmission Standard, http://www.loc.gov/standards/mets/), PREMIS (Preservation Metadata: Implementation Strategies, http://www.loc.gov/standards/premis/), and other elements of the digital archive infrastructure, and to develop procedures for handling audio files within the system.

Assuring access to audio content

Researchers often have difficulty discovering audio content, especially when the content is unique and cataloging or other descriptive metadata is lacking.  As with all archival materials, there is a tension between individual and collection-level cataloging, further complicated when a single physical audio object holds several intellectual entities, or a single intellectual entity is be spread over several physical objects.  Sometimes both situations exist simultaneously.  Finally, identification of content is dependent on playback when information on containers and labels is unreliable or incomplete, but many institutions lack playback equipment, and some physical objects are too fragile or deteriorated to risk playing before preservation takes place.

While United States copyright law permits re-recording of works currently under copyright for preservation purposes, the complications of intellectual property rights and permissions place obstacles in the way of researchers.  In many cases institutions either do not know who owns the rights to unique content or cannot locate the rights owner many years after the audio recording was created.  Much audio content is not in the public domain and can only be provided to listeners on-site at the owing institution rather than over the Internet for easy access.

Columbia Audio Preservation Efforts

All of these issues have implications for preservation of Columbia’s recorded collections.  Columbia’s Preservation and Digital Conversion Division has been actively preserving analog audio materials for over a decade, yet over 32,000 unique audio recordings have not yet been addressed.

In the 1990s and early 2000s we undertook major projects that produced analog preservation masters: the Language and Culture Archive of Ashkenazic Jewry (LCAAJ) consisting of 5,755 hours of audiotape field interviews with European Yiddish-speaking informants collected between 1959 and 1972, preserved through funds from the National Endowment for the Humanities (NEH), the New York State Program for the Conservation and Preservation of Library Research Materials, and several private foundations; and the NEH-funded Oral Histories of Twentieth-Century Politics project consisting of 1,013 hours of interviews from the era of Dwight Eisenhower, Robert Taft, and Adlai Stevenson conducted in the 1950s and 1960s.  A number of smaller projects were also accomplished during this period.

With the growing stabilization of audio digitization and the demise of high-quality analog audiotape, Columbia converted in 2005 to producing digital preservation masters.  Projects include the Ditson Fund Recordings Archive of 196 performances from the 1940s and 1950s of new American music by composers like Aaron Copeland and Virgil Thomson, funded by The GRAMMY Foundation®; the recently completed Union Theological Seminary project funded by the Lilly Endowment to preserve approximately 1,110 recordings from the Seminary’s archives dating from 1944 to 1975 and including speeches, lectures, and events involving figures such as Dietrich Bonhoeffer, Eleanor Roosevelt, and Martin Luther King Jr.; and several smaller projects funded internally by Columbia.

Our experience with digital conversion has entailed development of initial procedures for preparation of materials, vendor relations, and quality control.  However, we have identified significant gaps in our infrastructure that we share with other institutions, particularly in the areas of metadata capture and creation and in the interface between digital conversion and long-term preservation of the resulting digital files.  We have not been able to identify good models for building an effective infrastructure for digital audio preservation.

Infrastructure for Audio Digital Conversion and Preservation

The recent report of the NEH-funded project Sound Directions: Best Practices for Audio Preservation from Indiana University and Harvard does present a model for procedures and practices to address some of the issues discussed above, particularly collecting the appropriate metadata from the initial step of identifying an audio object for digital conversion through preparation for ingest into a long-term archive, and procedures for audio conversion labs.  The report will be useful to other institutions that have in-house labs and are seeking to develop a truly integrated approach to all the preservation functions.

Yet like Columbia, many institutions with audio holdings rely on external service providers for digital conversion and need guidance on procedures and best practices that differ in some respects from the fully in-house model that Sound Directions presents.  Institutions like Columbia must be able to:

- Deliver initial metadata to the service provider that clearly identifies each audio object, with as much useful data as is available on type, brand, duration, and physical problems; and this must be done in a format that the service provider can handle.  As noted above, especially with unique items, it can be very difficult for institutions to determine content/duration and other information.  Pre-existing information may be held in a variety of formats that are not immediately compatible, e.g., MARC records, lists in word-processed files or spreadsheets, online finding aids, or paper records.  Service providers differ as to what formats they can handle, and there are currently no best practices to guide institutions as they work with service providers.

- Receive back from the service provider both the digital content and the capture/ structural/technical metadata collected during the conversion process.  AES and other emerging standards require collection of a great deal of information about the original object and the conversion process, as well as about the digital files themselves.  Some of this can be collected automatically, but much requires manual input.  Digital conversion of audio is already quite expensive without paying providers to input large quantities of metadata; however, often they are the only ones with technical knowledge of the information, especially that which can only be discovered through playback.  There are currently no best practices in place to guide institutions in determining what metadata to request from service providers.  There are also no best practices on what formats to use for recording and delivering metadata, and service providers are faced with a wide range of demands from customers as to format, quantity, and style of metadata.

- Carry out quality control review on the digital files and on the metadata.  Many institutions lack the software and high-quality listening facilities to perform full quality control review of audio quality.  Quality control review of metadata can be equally time-consuming and complex.

Project Description

The Columbia University Libraries (CUL) proposes a two-year project, with work beginning in July 2008, to address a subset of the issues raised above:

- We will select a group of high-priority audio materials totaling 1,200 hours as a target for the project and will move them through the steps of digital conversion and metadata creation;

- We will attempt to build an infrastructure model for institutions that do not have an in-house audio conversion lab;

- We will collaborate with the authors of Sound Directions and with a leading service provider for audio preservation conversion to develop practices that are mutually functional for both content-owning institutions and service providers;

- We will disseminate the results of the project through written reports and presentations to appropriate professional organizations; and

- We will build and continually maintain a public project web site with full information about the project, including the final proposal and documentation created during the project.

The Columbia University Libraries

The Columbia University Libraries (CUL) is one of the top ten academic library systems in the nation, with 9.2 million volumes, over 65,650 serials, as well as extensive collections of electronic resources, manuscripts, rare books, microforms, and other nonprint formats. The collections and services are organized into 25 libraries, supporting specific academic or professional disciplines. The Columbia Libraries employs more than 400 professional and support staff to assist faculty, students, and researchers in their academic endeavors.

The services of the Libraries extend well beyond the university. Access to digital resources is provided through the Libraries’ web site (http://www.columbia.edu/cu/lweb). On-site access to the physical collections is available to anyone affiliated with members of the SHARES program under the auspices of OCLC and of the New York Metropolitan Reference and Research Agency. The Libraries also fill thousands of interlibrary loans through cooperative arrangements with OCLC, RAPID, the Regional Medical Library Center of New York, and others.

Selection of Materials

We will preserve 820 audiotapes from the Columbia Oral History Research Office (OHRO), comprising approximately 1,200 hours.  These items have been identified through our survey as simultaneously of the highest potential research value and at the highest risk for deterioration and loss.  The survey looked at a total of 4,974 reel-to-reel tapes and 9,766 cassettes from OHRO.  The set rated at the highest intellectual and local value and the worst physical condition (acute problems such as mold or broken/torn tape) totals 94 items amounting to approximately 130 recorded hours.  The set rated at highest intellectual and local value and second worst physical condition (serious problems such as shedding or vinegar odor) totals 726 items amounting to approximately 1,060 recorded hours.  In other words, the 6% of the OHRO collection that is both of highest research value and in the worst physical condition is targeted by this project.  Scholars are currently limited to the transcripts of these valuable resources because the analog recordings are so fragile that playback cannot be permitted.

Among the recordings identified for this project are oral histories with politically and socially active figures such as Nikita Khrushchev, Walter Lippmann, George Meaney, Clarence Mitchell, Nelson Rockefeller, Gloria Steinem, Robert F. Wagner; historians and literary figures such as James Baldwin, Jacques Barzun, Isaiah Berlin, William Buckley, Robert Heilbronner, Irving Howe, Anita Loos, Arthur Schlesinger Jr., Isaac Bashevis Singer, C. Vann Woodward; and members of the arts and entertainment community such as Judith Anderson, Gene Autry, Frank Capra, Joseph Cotton, Joel McCrea, Otto Preminger, Richard Rogers, Virgil Thomson, Mies van der Rohe, King Vidor.  Further description of the Oral History Research Office and its collections can be found in the appendix.

Importance of oral history for scholars

Scholars are increasingly turning to the sound of oral history for documentation of critically important political and social events in which it is important to rely on first-person sources both for information and for interpretation.  Oral history sources have grown central to work across disciplines in both the humanities and the social sciences.

While written transcripts sufficed in a world in which oral histories were perceived primarily as “documents,”—e.g., sources for citations and quotations in biographies or traditional histories—the increasing use of oral history as a central research methodology for understanding the intersection of history, politics, and culture requires access to the spoken word.  Sociologists, anthropologists, linguists, psychologists, and contemporary historians demand access to the voices of those who are interviewed, in order to judge for themselves the motivations and interpretations of innovators, political leaders, and those who bear witness to the critical events of recent times.

As recent OHRO initiatives demonstrate, it is critical that the sound as well as the transcript be fully accessible.  This means that the recordings themselves must be carefully preserved—a serious challenge given the short life-span of most recording media.  Yet, the defining feature of oral history is its attention to the distinctive qualities of voice, both literal and metaphorical, in their individual and collective forms.  Oral historians often argue that the only way we can be told about the broader meaning of the past is through the individual story.  One might equally argue that a story cannot be understood until it is “heard” in all its complexity and individuality.

Building an Audio Preservation Infrastructure

We will attempt to build an infrastructure model for institutions that do not have an in-house audio conversion lab, incorporating the applicable recommendations from the Sound Directions project and inviting Mike Casey and Bruce Gordon to serve as consultants to this project, and we will consider relevant work by other institutions and organizations.  In this process we will address some of the issues discussed above.

Technical and structural metadata

The project will develop procedures for collecting physical description and structural metadata in-house in a format that will integrate well throughout the digital conversion and preservation process.  All available information on the physical description about the tapes and cassettes (size/brand/type/duration/physical problems) has already been collected as part of the survey.  We will export this data from the MS Access survey database to the format we determine is best for the digital conversion process.  If necessary, we will develop procedures for converting metadata to/from our preferred format to any other format the service provider requires.

As is often the case with audio recordings, there is not a one-to-one correspondence between the physical carrier (the tape or cassette) and the intellectual content (the oral history).  The basic unit of an oral history is the session—a single interview period that typically runs from 1.5 to 2 hours.  Each session is a single intellectual object that can occupy one or more tapes, and each oral history consists of one or more sessions typically occurring over a period of days or months.  Interviewers often started the next session on the same tape immediately after the point where the previous session ended.  Occasionally empty space was used for an unrelated oral history.  In other words, many tapes have a track (“face” in the AES terminology) containing the end of one session and the beginning of another.  The project will create structural metadata to clearly identify all parts of each session and all sessions of each oral history, and it will organize the metadata to concatenate all data for a single session spread over more than one track of one tape.

Quality control and disposition of the original recordings

CUL’s current quality control procedures involve listening to a random sample of converted files in full; listening to a few minutes at the beginning, middle, and end of the rest of the files; and verifying the metadata.  We will review our quality control work station and procedures and upgrade as needed in the light of the recommendations in Sound Directions, AES, and other best practices.

After digitization, the original audio recordings will be returned to permanent storage at the Research Collections and Preservation Consortium (ReCAP), where they are currently housed.  ReCAP, located in Princeton, New Jersey, meets national guidelines for archival storage of magnetic media.

Providing access to the content

As the interviews are preserved, it is necessary to produce cataloging, finding aids, and other descriptive metadata to assist students, scholars, and the public at large to find and understand the content of the interviews.  Since OHRO routinely produces summaries of all of its interviews and projects, the task of documenting individual interviews has already been accomplished.  Individual MARC records for approximately 85% of the oral histories have already been added to OCLC WorldCat and to CUL’s online catalog CLIO, while most of the others are represented by manual summary sheets that contain all of the information needed for MARC records.

A small number of interviews lack descriptive information.  Project staff will first create MARC records for those original tapes that have none and will then derive MARC records for the digital versions.  All of the records will be loaded into CLIO and WorldCat.  For an example, please see the MARC record for the electronic version of an oral history with Edward Koch in the appendix.

OHRO maintains lists of its project and individual interviews on its home page (http://www.columbia.edu/cu/lweb/indiv/oral/index.html).  The project will add any of the preserved interviews that are not there already.

Rights and permissions

Intellectual property rights to the audio content of oral histories is held by the interviewees or their heirs.  When most of the oral histories to be included in this project were recorded decades ago, the then-current permissions agreements did not cover Internet access.  Unless this situation is addressed, researchers will only be able to listen to the preserved audio recordings on-site at Columbia.  In the interests of facilitating scholarly use of the recordings, we intend to review the permissions documents and to secure new legal agreements where necessary to enable online access.  In many cases this will require work with heirs and assigns.  OHRO has kept careful records of correspondence with all its narrators, which will enable this work to take place.

At the beginning of the project Kenny Crews, director of the new CUL Copyright Advisory Office, will review the standard OHRO permissions form.  Staff will then attempt to locate all the rights holders and update our permissions for use of the analog and digital audio content.  Rights and permissions metadata will be created for each preserved oral history.  We estimate that one-quarter of a staff person’s time over 18 months will be needed for this work.  CUL will pay these staff costs (and not use grant funds), since we believe it will be most efficient to deal with the permissions issues and resultant metadata during the preservation project.  The staff member’s first priority will be to accomplish the preservation work (preparation, quality control, and so forth) which is estimated to require 75% of a full-time schedule.  The staff member will concentrate on the permissions work during periods of time when there is a pause in those tasks while the materials are at the vendor being digitized.  If the permissions work cannot be completed within the project period, CUL will continue to support it afterwards.

Management and Long-term Preservation of the Digital Content

Once conversion is complete, the digitized files will be ingested into the CUL/Information Services (IS) local asset management system.  From there the files will be inventoried, given quality control review, enriched with additional metadata, exported and packaged in METS / PREMIS, and ingested into our long-term digital archive.

A key assumption of our proposed approach, and one that we hope to validate as part of this project, is that an effective local asset management system is a critical component for the success of medium- to large-scale multimedia digitization projects.  The asset management application should enable and facilitate tasks such as:  the semi-automated receipt and ingest of vendor-supplied digital files and metadata; the physical staging of large multimedia files; the performance of both inventory-level and object-level quality control; the ingest and storage of related external metadata documents and their correlation with the digital objects they describe; and the export of these digital objects and related metadata in a standard XML wrapper such as METS for ingest into a long-term digital archive or for export for some other purpose.

Asset management

Currently CUL’s plans for asset management entail the use of the open source “Alfresco” product (http://www.alfresco.com/), dSpace (http://www.dspace.org/), and/or Vfinity (http://www.vfinity.com/main.php).  dSpace is currently in production at Columbia for our institutional repository, and Alfresco has been installed for testing.  The Center for New Media Teaching and Learning (a division within CUL) will shortly be installing a test instance of Vfinity to evaluate its multimedia ingest and editing capabilities.  It is likely that our longer-term asset management strategy will be to migrate to a custom application built within Fedora or a Fedora-like architecture.

Long-term digital archiving

CUL will initially use the DAITSS (http://daitss.fcla.edu/) dark archiving software for our long-term digital archive.  Local implementation of DAITSS is now in the planning stages and is scheduled for fall 2008.  Here again we may in due course migrate from DAITSS into a Fedora-based LTA, although this is still under discussion and for the future.

Part of our effort during this grant project will be to develop procedures, workflows, and tools for the simple and efficient ingest, management, export, and long-term archiving of digital audio content.  Tasks we will need to accomplish, in conjunction where appropriate with our service provider, include:

- Identifying/developing a standard approach for receipt of vendor-generated multimedia files and vendor-generated metadata (as well as institutional metadata round-tripped and modified by the vendor);

- Determining how much and what metadata to incorporate into media file headers;

- Determining what subset of the PREMIS data elements should be created and stored in the metadata package;

- Determining the level and type of rights and permissions metadata to capture and in which format to express it, e.g., PRISM (Publishing Requirements for Industry Standard Metadata, http://www.prismstandard.org/) or Creative Commons;

- Determining the core set of descriptive, structural, and administrative metadata elements needed for multimedia asset management;

- Determining how more complex, externally created metadata can be stored, updated, and passed through the asset management system into other applications—and also perhaps used for raw keyword searching within the system itself;

- Conducting a task analysis of the manual activities required for the ingest and management of digital objects and designing and evolving a job description and set of procedures for a support-staff level data technician to perform this type of work.

Vended Services

We will collaborate with George Blood/Safe Sound Archive (SSA), a leading service provider for preservation conversion of analog audio materials, to produce high-quality digital copies of the recordings and to develop practices that are mutually functional for both content-owning institutions and service providers.  CUL has a history of working with preservation providers for mutual education and development of best practices, notably as a co-founder of the not-for-profit preservation microfilmer MAPS (later Preservation Resources, OCLC Preservation Service Center), and in our more recent work with a variety of text and imaging service providers.

SSA has been our audio conversion provider for several previous preservation projects, and we have developed a strong working relationship, including detailed discussions of appropriate metadata.  George Blood is a recognized expert in audio preservation, serving for instance as an advisor on the Sound Directions project.  As such, his company is a good partner for us in our effort to develop an infrastructure and practices that meet the institution’s needs of audio preservation in a way that makes reasonable demands on service providers.

While of necessity we will work with a single company during this project, the goal is to develop a model that is appropriate for any preservation service provider and not customized solely for SSA.  SSA will devote staff amounting to one FTE for one year to the planning and analysis effort. Among those participating will be George Blood, president of SSA, Preston Cabe, database manager, Jason Bachman, manager of quality assurance and information technology, and others.

In the first phase of the project, CUL will determine the structural, technical, and administrative metadata that we need for preservation management and long-term archiving, while SSA will identify the metadata they routinely collect, any additional metadata based on AES and other standards that they would recommend collecting, and the mechanisms they use to provide metadata to clients.  Together we will analyze the information and agree on how best to address any gaps between what is needed and what is currently provided.  We will collaborate to select one or more mutually functional exchange mechanisms that will integrate well throughout the process.  Mike Casey and Bruce Gordon will assist in this analysis process.

Digital conversion

SSA will convert the audio recordings according to current standards and best practices.  Each original sound unit (“face”) of a reel-to-reel tape or cassette that makes up part of a single session will be reproduced as a pair of master and delivery digital audio files.  When one face of a sound recording contains the end of one session and the beginning of a second (whether with the same interviewee on a different date or with a new interviewee), the two sessions will be reproduced in separate files.

Before digitization all original audio recordings will be reviewed and cleaned according to accepted standards as needed, without jeopardizing the materials.  Dry or defective splices on the original tapes will be cleaned and replaced.  Severely damaged tapes will be assessed for baking or other treatment to enable optimal transfer fidelity, and they will be worked on and converted one-by-one to assure maximum care.  Less-damaged recordings will be converted through semi-monitored transfer, under which two or three homogeneous recordings are converted in the same session.  Any recording whose condition renders it suspect will be fully monitored.

Preservation master files will be produced as an uncompressed pulse code modulated bit stream in Broadcast Wave format, at sampling frequency 96 kHz and 24 bit word length.  Delivery masters (also referred to as service or use files) will be derived from the master files, also in Broadcast Wave format but at sampling frequency 44 kHz and 16 bit word length.  Mono- or stereophonic configuration of the source item will be retained.  No digital enhancement will be performed on the master files, as the goal is an accurate copy of the original.  Filtering or noise suppression will be used only if obvious technical problems exist that seriously affect the intelligibility of the original recording.

Based on decisions reached during the planning phase of the project, SSA will enter appropriate metadata into the file headers and into spreadsheets or other formats for transmission to CUL.

Staffing Plan

Staff résumés and job descriptions are provided in the appendices, as is the Safe Sound Archive price proposal.

Contributed Columbia Staff

Janet Gertz, Director of the Preservation and Digital Conversion Division, will serve as the principal investigator overseeing the project.  She will participate in the workflow and metadata analysis, coordinate all project activities, assure that benchmarks and schedules are met, and handle all budgetary matters.  Dr. Gertz is currently managing the Project to Survey the Audio and Moving Image Collections of Columbia University, also funded by the Mellon Foundation, and she has managed all of CUL’s previous audio preservation projects.

Stephen Paul Davis, Director of the Libraries Digital Program Division, will manage technical infrastructure planning and implementation for the project, coordinating with other technology divisions of the Libraries/Information Services and the University, and participating in the workflow and metadata analysis.

OHRO Director Mary Marshall Clark has already provided research value ratings for the collections as part of the audio survey project.  She will continue to be available for any content-related questions and will deal with any policy-related issues that may emerge during the permissions work.

Music and Special Formats Cataloger Russell Merritt will manage creation of missing MARC records for the original interviews and creation of MARC records for all digital versions.

Grant-funded Staff

Corie Trancho-Robie, Assistant Director of OHRO, will serve as project coordinator for 5% of her time, managing directly the work of the project support staff.

Terry Catapano, Systems Analyst in the Digital Program Division, will spend 10% of his time over the course of the project on the design and planning of the project metadata, including conducting metadata analysis, planning, and testing, and he will also manage the development of scripts and tools needed for the semi-automated import and export of digital content, drawing as needed on other programming resources of the Libraries.  Procedures for support staff ingest and metadata quality assurance tasks will also be developed.

A technical assistant support position (assistant level 5) will be hired to carry out pre-processing of the recordings, input initial metadata, perform audio quality control, and perform other project-related duties over a period of eighteen months at a 75% rate.  CUL will pay the remaining 25% of salary and benefits for work relating to permissions.

A data archive technician support position (assistant level 6) will be employed for the equivalent of six months to perform ingest of the files, assign specified metadata elements, and carry out quality control on the digital documents and other project-related duties.

Project Vendor

George Blood/Safe Sound Archive of Philadelphia, Pennsylvania, will carry out digital conversion of the audio content, will create technical/structural/capture metadata, and will act as a partner in developing mutually acceptable procedures for the project.

Project Consultants

The co-authors of Sound Directions, Mike Casey, Coordinator of Recording Services of the Archives of Traditional Music at Indiana University, and Bruce Gordon, Audio Engineer of the Loeb Music Library at Harvard, will serve as consultants to the project.  In addition to reviewing Columbia’s proposed procedures in the light of their own investigation, they will attend a meeting at Columbia to share current information on technologies and methodologies in audio preservation.

Timeline

# 2008

July-December	Review CUL procedures.  Analyze metadata requirements.  Work with George Blood/Safe Sound and consultants to identify best procedures and mutually convenient information transfer formats.

July	Hire and train technical assistant 5.  Review OHRO permissions form.  Create project web site.

August-October	Begin retrieving recordings from ReCAP and preparing them for shipment to Safe Sound.  Complete MARC cataloging for all analog recordings.

November-December	Begin transferring metadata from survey database to project metadata format.

# 2009

January	Send pilot shipment of recordings and initial metadata to Safe Sound.

February	Receive back pilot shipment and technical/structural metadata from Safe Sound.  Carry out quality control review of audio and metadata.  Review procedures and adjust as necessary.  Meet with consultants and Safe Sound staff.

March-November	Hire and train technical assistant 6.  Continue preparing recordings and metadata for shipments to Safe Sound and continue carrying out quality control review on completed work.  Begin ingest.  Return completed recordings to ReCAP.  Create MARC cataloging for all digital recordings.

December	Receive back final shipment of recordings, complete all quality control, return all recordings to ReCAP.

# 2010

January-May	Create rights metadata for all digital recordings.  Create METS and PREMIS records and complete ingest of audio files and metadata into CUL digital asset management system for transfer to long-term digital archive.

June	Write project final report and make it publicly available.  Schedule presentations at appropriate professional meetings.

Outcomes

This project will result in the following outcomes:

- Preservation through digital conversion of 1,200 hours of seriously endangered analog audio recordings that have been identified as important for future research;

- Creation of cataloging records and other metadata to facilitate discovery of the preserved content by scholars, and to support preservation of the digital content;

- Establishment at CUL of a carefully designed and fully functional audio preservation infrastructure that is in compliance with current best practices and incorporates smooth working relations with an external service provider; and

- Creation and maintenance of a public web site with full information about the project, including the final project proposal and documentation created during the project.

As the project proceeds, we will disseminate our findings and approaches in real time to other institutions for their information and feedback via a wiki or blog as well as posting documents to the web site.  By project end, we will prepare technical documentation for the metadata components, system configurations, and implementation strategies as well as basic non-technical documentation for use by other institutions in planning and development of local procedures and workflows.  (Examples of CUL project web sites include the Audio/Moving Image Survey, https://www1.columbia.edu/sec/cu/libraries/bts/preservation/projects.html, and Digital Scriptorium https://www1.columbia.edu/sec/cu/libraries/bts/digital_scriptorium/index.html.)  We will also broaden awareness of the results of the project through presentations to appropriate professional organizations such as the American Library Association, the Society of American Archivists, and the Oral History Association.

Sustainability

Once procedures and infrastructure have been developed and vetted, we will use them as the routine basis for our future audio conversion and preservation.  Our goal over the next few years is to address preservation of the highest-priority recordings identified by the survey in the Rare Book and Manuscript Library, the University Archives, the Music Library, and other collections, as well as to provide on-demand conversion when researchers request access to specific analog recordings.

CUL earmarks a portion of its preservation budget annually for analog audio materials, and this amount will increase once we have a fully functioning infrastructure.  We are also in discussion with partners at several other institutions to address Columbia collections that are of particular importance to those institutions, and we will continue to seek additional funding from governmental and private sources.

Preserving Historic Audio Content:

Developing Infrastructures and Practices for Digital Conversion

The Columbia University Libraries

Appendices

- The Columbia Oral History Research Office

- MARC Record for Digitized Version of Edward Koch Oral History

- Job Descriptions

- CVs for Key Personnel

Appendix A

The Columbia Oral History Research Office

http://www.columbia.edu/cu/lweb/indiv/oral/index.html

The Columbia University Oral History Research Office (OHRO) is the oldest, and one of the largest, academic oral history archives in the world.  Founded by the Pulitzer Prize winning historian Allan Nevins in 1948 as an effort to document national and international politics, philanthropy, business, and culture, the archive now holds nearly 8,000 interviews amounting to 17,000 hours of recorded and transcribed conversation.

OHRO’s collections are extraordinarily valuable as a collective account of American history and politics in an increasingly international world, offering documentation from World War II, the New Deal era, the Cold War, and Vietnam, as well as most of the mayoral administrations of New York City. OHRO’s collections also offer a compelling portrait of New York City, from the oldest memory in the archive—which describes the draft riots during the Civil War—to the events of September 11, 2001.

Additionally, OHRO holds large collections in history of philanthropy, African-American history, women’s history, the history of journalism, the history of medicine and science, and the history of the arts, as well as biographical interviews with leaders in nearly every professional endeavor and substantial collections in Latin American and Chinese oral history.

While most oral history archives focus on local, regional, or institutionally specific histories, OHRO builds its collections for the broadest possible public use and relevance.  For example, OHRO recently captured nearly 600 hours of conversation detailing the impact and aftermath of September 11, 2001, on New York City communities.

Currently, OHRO is engaged in an audio project on the history of the Atlantic Philanthropies and a video history of the Council on Foreign Relations. The Notable New Yorkers Series, http://www.columbia.edu/cu/lweb/digital/collections/nny/index.html, provides complete audio access to ten of OHRO’s most important biographical interviews. Another recent online initiative, sponsored by the Carnegie Corporation, explores the history of Carnegie, with particular emphasis on South Africa, based on more than 700 hours of interviews taken between the 1960s and the 1990s. http://www.columbia.edu/cu/lweb/digital/collections/oral_hist/carnegie/

The Genres of Oral History

Oral history is a genre of documentary work in which historical research and biographical interviewing merge to create a unique interview form. Biographical in nature and historical in scope, an oral history is a portal into the living memory of the past, through which information, anecdote, and analysis combine to create a unique historical document.

The purely textual representation of the interview is no longer adequate in a multimedia scholarly environment. Students and scholars increasingly search for the nuanced interpretations of history through oral sources, due to a more qualitative turn in the social sciences and a greater appreciation of autobiographical and biographical sources throughout the academy.

To reflect this, Columbia University launched a new master of arts degree in oral history, scheduled to begin in the fall of 2008, the first master of arts in oral history in the United States. A major contribution to the creation of interdisciplinary research programs at Columbia, the program will be co-directed by Mary Marshall Clark, director of OHRO, and Peter Bearman of the Institute for Social and Economic Research and Policy, the research arm of the social sciences at Columbia University. Students will be trained to develop multi-media archives and documentary projects in which sound is a critical feature.

Through the master’s program and additional online initiatives, the educational uses of oral history archives will increase in importance, and the collections of recordings that already exist at Columbia will become even more significant to academic research—increasing the need to ensure wide and public access to the rich and varied collections held by the Oral History Research Office.

Appendix B

MARC Record for Digitized Version of Edward Koch Oral History

#### Edward I. Koch

| 000 | 03375cmm a2200553 a 450 |
| --- | --- |
| 001 | 5614541 |
| 005 | 20060620170124.0 |
| 006 | innn s t |
| 006 | aa s 001 0d |
| 007 | cr ana---¦¦n¦¦ |
| 008 | 060501s2006 nyu d eng d |
| 035 | __ ¦a (NNC)5614541 |
| 040 | __ ¦a NNC ¦c NNC ¦e dacs |
| 043 | __ ¦a n-us-ny ¦a n-us--- |
| 050 | _4 ¦a F128.5 |
| 100 | 1_ ¦a Koch, Ed, ¦d 1924- |
| 245 | 10 ¦a Edward I. Koch ¦h [electronic resource]. |
| 246 | 1_ ¦i Title on transcripts: ¦a Reminiscences of Edward I. Koch |
| 246 | 3_ ¦a Ed Koch |
| 260 | __ ¦a [New York, N.Y.] : ¦b Columbia University Libraries, ¦c 2006. |
| 538 | __ ¦a Mode of access: World Wide Web. |
| 500 | __ ¦a Title from home page (viewed May 1, 2006). |
| 580 | __ ¦a Forms part of: Notable New Yorkers. |
| 545 | __ ¦a Politician, congressman, mayor. |
| 500 | __ ¦a Includes audio recordings and transcripts of interviews conducted in 1975 and 1976. The site includes a biographical sketch and photo galley. The text of the transcripts are fully searchable, and a table of contents and name index are included. |
| 520 | __ ¦a In the 1960s and 1970s, Edward I. Koch served as Greenwich Village Democratic Party district leader, New York City Councilman, and U.S. Congressman for New York’s 17th and 18th districts. From 1978 until 1989 he served three terms as one of New York City’s most popular and outspoken mayors. The Edward I. Koch Administration Oral History Project includes interviews with almost eighty individuals, and most of these interviews were opened to the public in 2005. At the conclusion of the interviewing that took place during the 1990s, a symposium on memories of the Edward I. Koch administration was held at the New-York Historical Society. The audio recordings of speeches given that night to celebrate the history of Edward I. Koch and his mayoralty are posted here. |
| 500 | __ ¦a The web site was created as joint project of the Libraries’ Oral History Research Office and Libraries’ Digital Program Division. Columbia’s Digital Knowledge Ventures (DKV) provided site design, programming and consulting services. |
| 500 | __ ¦a Interviewed by Ed Edwin. |
| 600 | 10 ¦a Koch, Ed, ¦d 1924- ¦v Interviews. |
| 610 | 10 ¦a United States. ¦b Congress. ¦b House. |
| 610 | 20 ¦a Democratic Party (U.S.) |
| 650 | _0 ¦a Politicians ¦v Interviews. |
| 650 | _0 ¦a Legislators ¦z United States ¦v Interviews. |
| 650 | _0 ¦a Mayors ¦z New York (State) ¦z New York ¦v Interviews. |
| 651 | _0 ¦a New York (N.Y.) ¦x Politics and government ¦y 1951- |
| 651 | _0 ¦a United States ¦x Politics and government ¦y 1945-1989. |
| 651 | _0 ¦a United States ¦x Foreign relations ¦y 1945-1989. |
| 655 | _7 ¦a Oral histories. ¦2 ftamc |
| 655 | _7 ¦a Interviews. ¦2 ftamc |
| 700 | 1_ ¦a Edwin, Ed, ¦e interviewer. |
| 710 | 2_ ¦a Columbia University. ¦b Oral History Research Office. |
| 710 | 2_ ¦a Columbia University. ¦b Digital Knowledge Ventures. |
| 710 | 2_ ¦a Columbia University. ¦b Libraries. ¦b Digital Program Division. |
| 773 | 0_ ¦7 nnbc ¦a Notable New Yorkers ¦h [electronic resource]. ¦w (OCoLC65181290) |
| 852 | __ ¦a Columbia University. ¦b Oral history Research Office, ¦e Box 20, Room 801 Butler Library, New York, NY 10027. |
| 856 | 40 ¦u http://www.columbia.edu/cgi-bin/cul/resolve?clio5614541 |
| 920 | 40 ¦u http://www.columbia.edu/cu/lweb/digital/collections/nny/koche/index.html |
| 948 | 1_ ¦a 20060501 ¦b o ¦c rjb57 ¦d SCMC |
| 900 | __ ¦a AUTH |

Appendix C

Job Description for Newly Created Position

POSITION TITLE: Technical Assistant 5

A technical assistant support position (assistant level 5) will be hired to carry out pre-processing of the recordings, input initial metadata, perform audio quality control, and perform other project-related duties over a period of eighteen months at a 75% rate.  CUL will pay the remaining 25% of salary and benefits for work relating to permissions.

POSITION FUNCTIONS:

25%	Enter and edit preliminary descriptive information for individual interview sessions following established guidelines.

25%	Retrieve all selected tapes from ReCAP and track them throughout the project.  Create and maintain inventories, manifests, shipping lists, and other documentation.  Pack/unpack original tapes for pickup and return from vendor.

25%	Quality control:  Verify labels and content of service copy CDs; perform listening tests on CDs and fill out quality control forms; check metadata for accuracy and completeness.

25%	Following guidelines, generate rights and permissions form letters, research addresses of rights holders, track progress, and file responses.  Maintain statistics for all project activities.  Assist with related duties.

SKILLS:  Good hearing.  Good organizational skills and attention to detail essential.  Familiarity with spreadsheets and relational databases desirable.  Ability to maintain detailed records and to keep work flowing efficiently.  Ability to work independently when necessary.  Good intellectual and analytical skills that will contribute to overall project organization, communication with colleagues and timely project completion.

Job Description for Newly Created Position

POSITION TITLE: Technical Assistant 6

A data archive technician support position (assistant level 6) will be employed for the equivalent of six months to perform ingest of the files, assign specified metadata elements, and carry out quality control on the digital documents and other project-related duties.

POSITION FUNCTIONS:

30%	Transfer digital documents (including digital texts and audio) into CUL digital asset management system, both manually and in batch mode according to established procedures.

30%	Assign specified metadata elements to digital documents based on existing metadata and descriptions or on examination of the objects themselves.

20%	Quality control:  perform quality control procedures for both individual and sets of digital documents; check metadata for accuracy and completeness; verify inventories of digital files.

10%	Run specified software checks on digital documents to insure document safety (e.g. absence of electronic viruses) and integrity.

10%	Document issues and anomalies; help develop more efficient workflows and procedures; maintain statistics for all project activities.  Assist with related duties.

SKILLS:  Good organizational skills and attention to detail essential.  Familiarity with spreadsheets and relational databases.  Ability to maintain detailed records and to keep work flowing efficiently.  Ability to work independently when necessary.  Good intellectual and analytical skills that will contribute to overall project organization, communication with colleagues and timely project completion.

Appendix D

CVs for Key Personnel

Janet Gertz

101c Butler Library	(212) 854-5757

535 West 114th Street    	fax 212-854-9825

New York, NY 10027           	Gertz@columbia.edu

EDUCATION

1985		A.M.L.S. University of Michigan School of Library Science

1982		Ph.D.  Yale University, Indo-European Linguistics

HONORS

2008		Recipient, American Library Association Paul Banks and Carolyn Harris Preservation Award

EMPLOYMENT

2007-		Director, Preservation & Digital Conversion Division, Columbia University Libraries

1988-2007	Director, Preservation Division, Columbia University Libraries

1988		Preservation Microfilming Librarian, Columbia University Libraries

1985-1988	Special Collections Librarian/Humanities Cataloger, Pennsylvania State University Libraries

2001-present	Adjunct Professor, Introduction to Preservation, Palmer School of Library and Information Science, Long Island University

PROFESSIONAL ACTIVITIES

American Library Association (1983-present)

Preservation Policy Implementation Task Force (1992)

Association for Library Collections and Technical Services

Piercy Award Jury (1996-97)

Preservation and Reformatting Section

Nominating Committee (2007-08)

Photographic and Recording Media Committee (1994-96, 1999-2000, Chair 2001-03)

Audio Task Force (1994-98)

Photographic and Recording Media Discussion Group (Co-chair 2001-02)

Cooperative Preservation Programs Survey Task Force (Chair 1999-2001)

PLMS/RLMS Reorganization Task Force (Co-chair, 1993)

Chair (1993-94); Vice-Chair/Chair Elect (1992-93); Secretary (1989-92)

Joint PLMS/RLMS Reporting Session (Co-chair, 1991-92)

Association of College and Research Libraries, Rare Book and Manuscripts Section

Task Force to Review Guidelines on the Selection of General Collection Materials for Transfer to Special Collections (2004-present)

Statistical Survey Feasibility Committee (Chair, 1988-90)

American Society for Testing and Materials/Institute for Standards Research

Research Program on the Effects of Aging on Printing and Writing Papers

Advisory Committee (Technical Advisor, 1997-2002)

“Assessing the Value of the WGBH Media Library and Archives for Scholarly Use,” WGBH Boston, Mellon Foundation-funded project, Advisory Council (2006-2007)

Commission on Preservation and Access, Preservation/Science Council (1992-97)

Janet Gertz

“Developing Principles and Methodologies for Moving Image and Audio Preservation in Research Libraries," New York University Mellon Foundation-funded project, Research Council (2006-2007)

“Developing Standardized Metrics: Towards Understanding the Impact of College and University Archives and Special Collections on Scholarship, Teaching, and Learning,” University of Michigan/University of Toronto/University of North Carolina Mellon Foundation-funded project, Advisory Council (2005-2007)

Digital Library Federation

Collection Strategies Advisory Group (2000-01)

Digital Imaging Benchmarks Advisory Group (2001-02)

Digital Registry Project Team (2002)

National Information Standards Organization

Standards Development Committee (1999-2002)

Sub-Committee AU, Draft Standard ‘Technical Metadata for Digital Still Images’ (1999-2002)

New York State Conservation/Preservation of Library Materials Program

Columbia University Libraries Representative (1989-present)

Executive Committee (1996-99; Chair 1997-99)

Northeast Document Conservation Center, Curriculum Advisory Council (1999-present)

Research Libraries Group

RLG/DLF Task Force on Policy and Practice for Long Term Retention of Digital Materials (1999-2000)

Preservation Advisory Council (1992-95; Chair 1994-95)

Preservation Committee (1988-91)

SOLINET, Preservation Advisory Committee (2004-present)

RECENT PUBLICATIONS

“Audio Preservation and the LCAAJ Archive at Columbia University,” in The Language and Culture Atlas of Ashkenazic Jewry, Tübingen: Max Niemeyer, forthcoming 2008

“Preservation and Selection for Digitization,”  Leaflet series, Andover, MA: Northeast Document Conservation Center, 2007

“RLG Guidelines for Microfilming to Support Digitization,” Supplement to RLG Microfilming Publications, with Lars Meyer.  RLG, 2003.

“Selection for Preservation in the Digital Age: An Overview,” LRTS 2000; also printed in Microform & Imaging Review 2001

“Vendor Relations,” Chapter 7 of Handbook for Digital Conversion Projects:  A Management Tool, Andover, MA: Northeast Document Conservation Center, 2000

RECENT PRESENTATIONS

“Selection for Digitization,” Northeast Document Conservation Center School for Scanning, annually 2000-07

“Columbia’s Audio-Visual Survey Instrument,” Assessment and Prioritization Program, Association of Moving Image Archivists, Rochester NY, September 28, 2007

Janet Gertz

“The Columbia Audio-Visual Survey,” PARS Recording Media Group, Washington DC, June 24, 2007

“Selection and Program Management,” ALCTS Digital Asset Management Program, Washington DC, June 23, 2007

“Library Binding and Working with Library Binders,” Metro Symposium, New York NY, May 14, 2007

“Digital Preservation Policies,” Preservation Administration and Reformatting Section, ALA Midwinter Conference, Seattle, January 20, 2007

“Preservation in the Twenty-First Century,” Independent Research Libraries Association, New York Academy of Medicine, June 1, 2006

“Preserving the Language and Cultural Atlas of Ashkenazic Jewry Audiotape Archive at Columbia University,” EYDES program “Jiddisch und die Mitte Europas,” Berlin, Germany, April 28, 2005

“Digital Preservation Policies in Academic Institutions,” Society for American Archivists program “Preservation Policies for Digital Resources,” Boston, MA, August 6, 2004

“Preservation for Special Collections: What’s Current and What’s to Come,” seminar at the Rare Book and Manuscripts Section (ACRL) Preconference, New Haven, CT, June 22, 2004, with Charlotte B. Brown

“Outsourcing:  Working with Vendors,” Metro Digitization Symposium, New York NY, March 11, 2004

“Selection in the Digital Age,” Missouri Digitization Conference, Independence, MO, February 12, 2004

“Management Skills:  Project Management and Contracting with Vendors,” Northeast Document Conservation Center Program Managing Preservation, Andover, MA, September 12, 2003

“Disaster Preparedness Issues in Academic Libraries,” Special Libraries Association, New York, NY, June 9, 2003

“NISO Draft Standard ‘Technical Metadata for Digital Still Images’,” RLG Forum “Converging, Emerging Standards for Digital Preservation,” Atlanta, GA, June 16, 2002.

“Surveying Stack Collections,” ALCTS Program “Dirty Books:  Stacks Cleaning in Libraries,” Atlanta, GA, June 15, 2002.

“What Should We Save?  Preserving Electronic Resources in Research Libraries,” 4th ARSAG International Symposium, Paris, France, May 27, 2002.

“Preservation Management of Local History Projects,” Symposium on Preserving Andrew Carnegie’s Legacy, Pittsburgh PA, May 17, 2000.

Stephen Paul Davis

# Experience

Columbia University Libraries

Director, Libraries Digital Program. Lead and manage the Columbia's Libraries Digital Program. Coordinate planning and design of new digital program and oversees implementation of initiatives. Represent the Libraries in campus, national and regional meetings relating to digital libraries. A member of the Libraries' senior management team, reporting to the Deputy University Librarian. Supervise Digital Program Division, with 6 FTE.  (2003-present)

Assistant to the Deputy University Librarian for Digital Library Implementation.  Responsible for technology coordination, planning and implementation within Columbia's digital library program. (2000-2002)

Director, Library Systems Office.  Chief systems officer of the Libraries for all phases of systems and automation planning, implementation and management. Oversee and coordinate operation of library computer systems, coordinate plans and activities with other units of the University e.g., Academic Computing, Administrative Information Services, Communications Services); manage Library Systems Office staff (12 FTE). Coordinate library-related mainframe, Unix and PC systems. Participate in Library policy planning, digital library initiatives & WWW implementation. (1987-2000)

Health Sciences Library. Head, Acquisitions/Serials Dept. Supervise 6 FTE. Manage use of RLIN acquisitions and Faxon LINX serials control systems. Manage expenditure of acquisitions budget of $800,000/year. Planning responsibilities. Some selection and collection development responsibilities. Developed database applications to support serial acquisitions & shadow fund accounting. (1985-1987)

Library of Congress

Senior Network Research Analyst/Network Specialist, Network Development & MARC Standards Office. Research and analysis of topics in library information systems and networks; preparation of research reports, system specifications, international MARC record conversion requirements, online cataloging input assistance specifications; project coordination, monitoring contracts with private vendors; research work in copyright of machine-readable information, international transborder data flow, international exchange of MARC records, standards for bibliographic holdings information. Worked on MARC format integration, multiple versions proposal, MARC holdings format, revised visual materials format, archival control format. (1982-1985)

LC Intern Program. Intensive orientation to the history, organization, functions, and management concepts of the Library of Congress. (1981-1982)

New York Public Library

Assistant to the Project Director for Systems, Operational Test of the Eighteenth Century Short Title Catalogue Project. Developed requirements and procedures for machine-assisted cataloging system for international cataloging project. (1978)

Education

Columbia University, School of Library Service. M.S., May 1978, in Information Science. Scholarship. Graduated with Honors, awarded Wheeler Prize for Outstanding Achievement.

Yale University, Graduate School of Arts and Letters. M.A., 1976. Dept. of Germanic Languages & Literatures.

Yale College. B.A., 1974. Major in German Literature, minor in Psychology. Full scholarship as Yale National Scholar. Cum laude, with departmental honors. Awarded Scott Prize for senior thesis.

Stephen Davis

National Committees

National Digital Library Federation, Metadata Task Force (1997).

ALA Association for Library Collections & Technical Services, ALCTS Task Force on Meta Access (1996-97).

ALA MARBI Committee (RTSD/LITA/RASD Representation in Machine-Readable Form of Information Committee). Member (1987- 1991). Chair (1989-1991).

NISO Subcommittee W on Non-Serial Holdings Statements. Chair (1983-1989).

ALA ACRL Rare Books & Manuscripts Section, Standards Committee. (1979-84).

Journal of Library Automation, Editorial Board, Library and Information Technology Association, ALA. Member (1979-81).

Independent Research Libraries Association, Ad Hoc Committee on Standards for Rare Book Cataloguing in Machine-Readable Form. Secretary (1978-79).

Selected Publications & Lectures

Digital Libraries

"Digitizing a Small Collection of Relatively Well-Behaved Monographs, or, Where Are NetLibrary, Questia and Ebrary When You Need Them?" [slides] – NY METRO Digitization Symposium, 7/2002.

Book Review: "Digital Futures: Strategies for the Information Age," D-Lib Magazine 8:4, April 2002.

"Integrating Access to Electronic Resources" [slides] – NY METRO Workshop on Building Library Webs, 10/21/1998.

"Managing & Accessing the Digital Library" [slides] – A presentation at New York Public Library, 4/23/1998.

Systems & Technical Services

"HILCC, A Hierarchical Interface to Library of Congress Classification : a project report on the development of an operational prototype LCC-based subject interface to electronic resources at Columbia University Libraries." Journal of Internet Cataloging, v.5, no 4 (2002), p. 19-49.  Link to preprint version.

"A Relational Database Approach to Metadata." – With David Millman; project briefing at the Fall 1997 Coalition for Networked Information Task Force Meeting, Minneapolis, MN.

"Image Metadata: Desiderata for a Manageable Future" [slides] - A presentation delivered at the ASIS 1996 Annual Meeting.

"SGML-MARC: Incorporating Library Cataloging into the TEI Environment." -- A presentation delivered on March 23, 1996 at the workshop on The Text Encoding Initiative Guidelines and Their Application to Building Digital Libraries, held in conjunction with the First ACM International Conference on Digital Libraries., Bethesda, Maryland.

"Next Generation Dis-Integrated Library Systems." - A presentation delivered on Thursday, Oct. 12, 1995, at the NOTIS Users Group Meeting, Chicago, IL.

"Digital Image Collections: Cataloging Data Model and Network Access," In: RLG Digital Image Access Project: Proceedings From an RLG Symposium Held March 31 and April 1, 1995, Palo Alto, California. Edited by Patricia A. McClung. Palo Alto, CA: RLG, 1995. P. 45-59.  Link to preprint version

Presentation on Bibliographic Access to Electronic Images, RLG Digital Image Access Project, March 1995.

Presentations on Future of MARC: NE Technical Services Librarians, Worcester, MA, April 1991; Health Sciences OCLC Users' Group, Washington, DC, April 1991; NY Library Association, NYC, Nov. 1991.

Special Collections Automation

"Bibliographic Control of Special Collections: Issues and Trends," Library Trends (Summer 1987).

"Computer Technology as Applied to Rare Book Cataloguing," IFLA Journal, 10:2 (May 1984), p. 158-169. Based on a paper delivered at the 1983 IFLA International Meeting, Munich, West Germany.

"Recent Work in Automation and Rare Books," in Rare Books, 1983-84: Trends, Collections, Sources. New York: Bowker, 1984, p. 109-120.

VanWingen, P. and S.P. Davis. Standard Citation Forms for Published Bibliographies and Catalogs Used in Rare Book Cataloging. [1st ed.]   Washington: Library of Congress, 1982.

Bibliographic Description of Rare Books. Washington: Library of Congress, 1981. Co-author.

Belanger, T. and S.P. Davis. "Rare Book Cataloguing and Computers." Parts I and II. AB Bookman's Weekly. Feb. 5, 1979 & Jan. 14, 1980.

Davis, S.P., ed. Proposals for Establishing Standards for the Cataloguing of Rare Books ... in Machine-Readable Form: Final Report. Worcester, Mass.: Independent Research Libraries Association, Committee on Rare Book Cataloging in Machine-Readable Form, 1979.

Corie Trancho-Robie

259 Van Brunt Street #4, Brooklyn, NY 11231  |  (917)-803-6735  |  ctrobie@columbia.edu

EDUCATION

Columbia University, New York, N.Y.

M.A., American Studies, expected 2008

Smith College, Northampton, M.A.

B.A., Education & Child Study, 1999

WORK EXPERIENCE

Columbia University, New York, N.Y. 	2005 to present

Assistant Director, Oral History Research Office

- Daily management of oral history projects and grants, including interview processing, submissions and supervision of part, full, graduate and other office staff.

- Provide assistance to director with future project planning and cultivation of external partnerships.

- Management and review of office and project financial reports, budget tracking, forecasting and payroll.

- Development and maintenance of office workflow for digital projects in collaboration with digital preservation departments.

Project Coordinator, Oral History Research Office	2005 to 2007

- Supervised production of oral history digital files, transcripts, audit-editing and preservation of interviews pertaining to the Atlantic Philanthropies Oral History Project, a 500-hour history that charts the development and activities of a major philanthropic organization.

- Developed and maintained project databases, track progress in liaison with financial services and generate regular progress reports.

- Managed and supervised graduate assistants and casual staff.

- Administered technical assistance, training and planning support to interviewers and other OHRO staff.

New Visions for Public Schools, New York, N.Y. 	2001 to 2005

Knowledge Management Officer 	2004 to 2005

- Liaison between organization’s five departments through the use of informal internal reports and news, as well as professional development to staff on methods for knowledge sharing around relevant issues concerning New York City’s children, educators, and schools.

- Oversaw design, structure, and implementation of data collection, including field notes, school performance data, and survey tools, used internally for program progress analysis and externally for reporting to schools and funders.

- Supervised staff and interns in analysis of data to support and enhance organizational communication, collaboration and program planning.

Corie Trancho-Robie

Program Officer 	2001 to 2004

- Coordinated 24 New York City public schools for Tech Power, a competitive grant program, designed to help teachers and students become proficient users of technology.

- Managed the program’s community outreach, RFP process and proposal review.  Wrote regular project status reports.

- Supported and advised teachers on the design and implementation of technology professional development programs in their schools.

- Assisted in collection of data pertaining to New York City high school facilities for the New Century High Schools Initiative.  Analyzed school facility data for the use in transforming existing campus buildings, new strategies for student capacity, and innovative structural space designs.

New York Networks for School Renewal, New York, N.Y.	1999 to 2001

Senior Program Officer

- Assisted in the coordination and management of four education reform organizations working to create more than 100 small public schools in New York City.

- Wrote quarterly and annual reports for benefactors and education policy officials.

- Coordinated site visits to schools for benefactors and education policy officials.

- Helped develop and oversee a teacher training and support program for first-year teachers.

- Managed the organization’s conference on public school reform.

RELATED INTERESTS

Researcher/Interviewer, Officer’s Row Project	2004 to Present

Lead interviewer and researcher on project designed to document and preserve the history of the officers’ quarters of the Brooklyn Navy Yard through the process of oral history, photography and urban memory.

Merit Panel Reviewer, National Science Foundation	2004

Read, reviewed and discussed grant applications focusing on science, technology, engineering, and mathematics for the Information Technology Experiences for Students and Teachers (ITEST) federal grant program.

Reviewer, Fund for Teachers Summer Grant Program	2002 to 2005

Read, reviewed, and discussed grant applications aimed at promoting and supporting educator-led summer learning opportunities.

Reviewer, Champions of Active Learning National Grant Program 	2002 to 2005

Read, reviewed, and discussed grant applications designed to encourage and support innovative instructional programs that result in improved achievement for middle grade students.

Reviewer, Citicorp College Bound Grant Program	2001 to 2005

Read, reviewed, and discussed grant applications designed to help build high-quality college preparation infrastructures that give all students an opportunity to pursue higher education and prepare for life after high school.

International Association of Sound and Audiovisual Archivists, Technical Committee.  2004.  Guidelines on the Productions and Preservation of Digital Audio Objects, IASA-TC 04.  Aarhus, Denmark: IASA.

See for instance:  Audio Engineering Society, Standards Committee.  2007.  Draft Standard for Audio Preservation and Restoration - Administrative and Structural Metadata for Audio, AES-X098 SC-03-06-B.

Mike Casey and Bruce Gordon, 2007.  Sound Directions: Best Practices for Audio Preservation.  http://www.dlib.indiana.edu/projects/sounddirections/bestpractices2007