## Sheet1
Human Rights Portal Project - 10/3/2011 | 2011 Q3 | 2011 Q4 | 2012 Q1 | 2012 Q2 | 2012 Q3
1. Phase 1
1.1. Document metadata requirements
1.2. Develop metadata search system
1.3. Document web search requirements
1.4. Develop web search system
1.5. Launch Phase 1 protal prototype
1.6. Perform selected user testing
1.7. Ingest Web Archive files into Fedora
Phase 2
2.1. Iterate development & testing
2.2. Identify additional data sources
2.3. Create local document repository
2.4. Incorporate additional data sources
2.5. Launch public beta
2.6. Perform selected user testing
Phase 3
3.1. Complete / reengineer indexing system
3.2. Iterate development & testing
3.3. Explore enhanced indexing techniques
3.4. Implement enhanced indexing techniques
3.5. Perform selected user testing
3.6. Launch public release 1.0
Phase 4
4.1. Explore linked data options
4.2. Prototype linked data options
4.3. Perform selected user testing
4.4. Address results of user testing
4.5. Incorporate linked data into public release
4.6. Launch public release 2.0
4.7. Set up ongoing Web archiving workflow